## TestPlan ScreenReader
Test Planner and Tracker |  |  | ProjectName WASM OS
Remove sample items before submitting this.
Test No. ID | Trace to User Story ID and Name | Pre-conditions | Test Description (steps) | Expected Outcome | Sprint 1Outcome | Sprint 2 Outcome | Sprint 3 Outcome
1 | As a developer, I want to upload a .wasm file to the runtime so it can be prepared for execution. | The backend server prototype is running. The user has access to the "complete" web UI. | Test 1.1: Using the web UI, upload a valid .wasm file. Test 1.2: Using the web UI, attempt to upload a non-.wasm file. |  | Wrote the skeleton code. | The basic file upload component was verified.
2 | As a developer, I want the runtime to correctly execute the bytecode of a simple WASM module. | The Rust core VM and parser are built. A simple test file (add.wasm) is available. | Create a unit test that loads and executes the add.wasm file. Verify the VM correctly interprets the opcodes (local.get, i32.add) and produces the correct result. |  |  | The core "steel thread" unit test was implemented and passed. This proves the interpreter prototype works.
3 | As a backend developer, I need the Go orchestrator to communicate with the Rust core engine. | The Go backend and Rust core are set up. The FFI bridge is defined. | Test 3.1 (FFI): Write a test in the Go backend to call a "hello_world" function in the Rust core. Test 3.2 (API Proto): Stub out the GET /api/tasks endpoint in the Go backend to return a hardcoded (fake) JSON response. |  |  | Both tests passed, proving the Go/Rust FFI connection is working and the backend API prototype is reachable.
4 | As a user, I want to use the web dashboard to see a list of my WASM tasks. | The "complete frontend" (web UI) is deployed. The "prototype backend" (Go/Rust) is running and exposing the stubbed API (from Test ID 03). | Load the web UI in a browser. Verify the dashboard successfully calls the GET /api/tasks endpoint and correctly displays the fake (prototype) data from the backend. |  |  | The "complete frontend" was successfully tested against the "prototype backend." The UI correctly renders the stubbed data, proving the integration path is valid.
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29