## TestPlan ScreenReader
ProjectName WASM OS
Remove sample items before submitting this.
Test No. ID | Trace to User Story ID and Name | Pre-conditions | Test Description (steps) | Expected Outcome | Sprint 1Outcome | Sprint 2 Outcome | Sprint 3 Outcome
1 | As a developer, I want to upload a .wasm file to the runtime so it can be prepared for execution. | The backend server prototype is running. The user has access to the "complete" web UI. | Test 1.1: Using the web UI, upload a valid .wasm file. Test 1.2: Using the web UI, attempt to upload a non-.wasm file. |  | Wrote the skeleton code. | The basic file upload component was verified.
2 | As a developer, I want the runtime to correctly execute the bytecode of a simple WASM module. | The Rust core VM and parser are built. A simple test file (add.wasm) is available. | Create a unit test that loads and executes the add.wasm file. Verify the VM correctly interprets the opcodes (local.get, i32.add) and produces the correct result. |  |  | The core "steel thread" unit test was implemented and passed. This proves the interpreter prototype works.
3 | As a backend developer, I need the Go orchestrator to communicate with the Rust core engine. | The Go backend and Rust core are set up. The FFI bridge is defined. | Test 3.1 (FFI): Write a test in the Go backend to call a "hello_world" function in the Rust core. Test 3.2 (API Proto): Stub out the GET /api/tasks endpoint in the Go backend to return a hardcoded (fake) JSON response. |  |  | Both tests passed, proving the Go/Rust FFI connection is working and the backend API prototype is reachable.
4 | As a user, I want to use the web dashboard to see a list of my WASM tasks. | The "complete frontend" (web UI) is deployed. The "prototype backend" (Go/Rust) is running and exposing the stubbed API (from Test ID 03). | Load the web UI in a browser. Verify the dashboard successfully calls the GET /api/tasks endpoint and correctly displays the fake (prototype) data from the backend. |  |  | The "complete frontend" was successfully tested against the "prototype backend." The UI correctly renders the stubbed data, proving the integration path is valid.
5 | As a user I want to parse a wasm file, the wasm engine should successfully convert leb values to u32, f32 and I32 | A string of leb bytes should be given to leb_tou32(), leb_toi32 and leb_tof32 from a cursor | Test 7.1 Call leb_tou32 from a cursor supplied with leb bytes.Test 7.2: Call leb_toi32 from a cursor supplied with leb bytes Test 7.3: Call leb_tof32 from a cursor supplied with leb bytes
6 | As a user I want to parse a wasm file. The parser should parse any valid files for me. | A cursor is supplied with the bytes of a wasm file and parses them | Test 8.1: Call parse wasm on the minimum size wasm which is 8 bytes. Test 8.2 the parser should return gracefully apon parsing a invalide wasm file. Test 8.3: The parser should handle a wasm with bad bits gracefully returning to start wasm funcion
7
8 | UNIT-007 :Syscall ID Range Check | sys_call_test.rs is compiled; Mock syscall ID is provided. | 1.Input:the test provides a mock syscall ID. 2.The test asserts the ID is within the valid range | the test muss PASS, confirming that internal syscall IDs are managed within a defined,reasonable range. |  | code green: passed core syscall ID check implemented and passing.
9 | UNiIT-008:Task Queueing Basic | scheduler_test.rs is compiled ;Task queue is initalized. | 1.Input :A task queue is initalized with elements. 2.The test asserts the final length is 3 and the first ID is 1 | the test muss PASS, confirming that scheduler's queue structure correctly stores elements and preserves the order/ID of task | code yellow :Queue handles basic insert ions but fails round- robin test. | code green: passed all queueing tests passed.
10 | UNIT-009:WASM FILE Extension Check | module_loader_test.rs is compiled; Filenames provided for testing. | 1.Input :Test provides a filename ending in .wasm 2.Input :Test provides a non-WASM filename. 3. The test asserts that rejection logic is correct . | Both assertions must PASS, confirm ing the module loader correctly accepts only files ending in .wasm and rejects non-WASM files. | code yellow :Some process fails | code green: PASSED
11 | Core -007 :Basic Arithmetic (test_add.rs) | File:test_add.rs is compiled to WASM | Executes the fixed addition,checks the result against 30,and logs the outcome | the test module must pass confirm ing that the WASM runtime correctly executes basic arithmetic and conditional branch |  |  | code green:Passed
12 | Core-008:Loop&Iteration (test _loop.rs) | Filele:test_loop.rs is compiled to WASM | Executes a fixed for loop, asserts the final sum is 15, and logs the status using host_log | the test modulemust pass confirming WASM runtime correctly handles iterative control flow structures |  | code red:Loop execute infinitely | code green:Passed
13 | Core-009:Host Communication (test.rs) | File:test.rs is compiled to WASM | Loads the WASM module and verifies successful host-guest communication | the test must pass , confirming that WASM runtime successfully handles calls to imported functions |  |  | code green:Passed
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29